MINISTRY OF
MECHANICAL AFFAIRS

Implementation Plan

Steampunk Game Jam • Godot 4 • GDScript • Solo development • 48-hour target

HIGH-LEVEL GOAL Build a complete, intentionally inconvenient but reliably playable top-down steampunk bureaucracy game. The player must obtain a steam-operating permit from a disastrously overengineered Ministry, only to discover the permit was never needed.

Design principle: automate the coding, not the verification.

# 1. Project Summary

The Ministry of Mechanical Affairs is a top-down comedy adventure set in a Victorian-inspired steampunk institution. The player is a junior clerk who must obtain a permit to operate a steam-powered machine before the closing bell. Every department adds paperwork, stamps, queues, fees, mechanical puzzles, and increasingly absurd regulations. The final reveal: the machine has been decommissioned since 1847, so the permit was unnecessary.

| Genre | Top-down comedy adventure / inconvenience simulator |
| --- | --- |
| Engine | Godot 4 |
| Language | GDScript |
| Visual direction | Blueprint diagrams, technical annotations, brass/amber highlights |
| Target playtime | 8–12 minutes; fallback 5–8 minutes |
| Team | Solo developer using Antigravity for AI-assisted implementation |
| Deadline | 48 hours |
| Primary success criterion | A complete, stable, funny game with an intentional bad-design identity |

# 2. Core Design Principles

The player must always be able to identify the current objective.

Bad design should be deliberate, consistent, and funny—not broken or arbitrary.

The player may be delayed, misled, fined, or inconvenienced, but must not become permanently softlocked.

Every major mechanic should create a joke, a decision, or a memorable interaction.

Aim for a new beat every 30–60 seconds: a rejection, rule change, machine failure, meeting, or absurd interaction.

One compact floor with connected areas is better than a large unfinished world.

Protect testing and submission time; no new features in the final six hours.

# 3. Premise and Core Gameplay Loop

The Ministry controls all steam-powered machinery in the empire. Even a tiny engine requires a permit bearing multiple official seals. The player is a junior clerk tasked with obtaining the permit before the Ministry closes.

Receive the objective: obtain Permit Form 27-B.

Explore the Ministry and visit counters, clerks, and machines.

Collect forms, stamps, tokens, and queue tickets.

Complete short mechanical tasks and pressure puzzles.

Trigger increasingly absurd regulations and survive a compliance audit.

Submit the permit before the closing bell.

Discover the target machine has been out of order since 1847 and never needed a permit.

# 4. Level Plan: One Floor, Six Functional Areas

1. Reception and Queue Hall: Spawn point, objective board, ticket machine, starting currency, tutorial, closing clock.

2. Department of Forms: Collect Form 27-B, learn that it is obsolete, receive Form 27-B-Rev.2; inventory and pneumatic tube.

3. Seal and Stamp Office: Obtain required seals, pay a fee, complete a short stamp-alignment minigame.

4. Steam Regulation Chamber: Solve a deterministic three-valve pressure puzzle to power a pneumatic delivery system.

5. Compliance and Audit: Meet the mechanical inspector, trigger a rule change, endure a mandatory meeting.

6. Permit Registry and Final Machine: Submit completed documents, receive the permit, discover it was unnecessary, show ending and credits.

Implementation note: these are logical areas inside one main gameplay scene, not six separate scenes. This reduces transition and integration work.

# 5. Selected Mechanics and Implementation Mapping

| Mechanic | Implementation |
| --- | --- |
| Pneumatic paperwork | Inventory items, interaction targets, scripted delivery; tube can occasionally send a document to the wrong desk. |
| Stamp collection | Inventory items and permit requirements. |
| Mechanical queues | Small state machine and timer; missed queue can always be rejoined. |
| Steam pressure puzzles | Three valves, a pressure gauge, and a target range; deterministic solution. |
| Malfunctioning automata | NPC interaction plus conditional dialogue. |
| Escalating regulations | Regulation manager with predefined event triggers. |
| Clockwork inventory | Small fixed-slot inventory; defer complex item shapes. |
| Overengineered machinery | Multi-step interactions using shared interaction logic. |
| Mandatory meetings | Short timed dialogue interruption; never permanently traps the player. |
| Administrative currency | Integer balance, configurable fees, and a repeatable recovery source. |
| Cursed controls | One or two context-sensitive changes with clear recovery instructions. |
| Mechanical minigames | Reusable small input-and-check panel. |
| Closing bell countdown | Global timer; timeout causes overtime/penalty rather than an unwinnable state. |
| Compliance inspector | Requirement validator with absurd but actionable rejection messages. |
| Awful physical design | Deliberately obstructive desks and doors that remain traversable. |

# 6. Feature Priorities

## Must ship

Top-down movement and collision

Interaction prompt and common interactable interface

Objective tracker and quest state

Inventory, stamps, and currency

Permit validation and final reveal

Dialogue, restart, and basic audio

One queue and one short puzzle

## Add after the core loop works

Escalating regulations

Compliance inspector

Closing countdown

One mandatory meeting

Mechanical minigame

More elaborate blueprint UI and sound

## Cut first if behind

Complex inventory shapes

Sophisticated physics

Multiple endings

Additional floors

Advanced control sabotage

Extensive branching dialogue

# 7. Technical Architecture

## Suggested project structure

ministry-of-mechanical-affairs/
├── project.godot
├── scenes/
│   ├── main_menu.tscn
│   ├── ministry.tscn
│   ├── player.tscn
│   ├── npc_clerk.tscn
│   ├── inspector.tscn
│   ├── interactable.tscn
│   ├── pressure_puzzle.tscn
│   └── ending.tscn
├── scripts/
│   ├── player_controller.gd
│   ├── interactable.gd
│   ├── game_manager.gd
│   ├── objective_manager.gd
│   ├── inventory_manager.gd
│   ├── regulation_manager.gd
│   ├── interaction_manager.gd
│   ├── dialogue_manager.gd
│   ├── ui_manager.gd
│   └── systems/
│       ├── queue_system.gd
│       ├── pressure_puzzle.gd
│       └── minigame_controller.gd
├── ui/
│   ├── hud.tscn
│   ├── inventory.tscn
│   ├── dialogue_box.tscn
│   ├── objective_panel.tscn
│   └── minigame_panel.tscn
├── assets/
│   ├── sprites/
│   ├── fonts/
│   ├── audio/
│   └── materials/
└── data/
    ├── items.json
    ├── objectives.json
    ├── regulations.json
    └── dialogue.json

This is a logical starting structure, not a requirement to create every file. Combine small scripts where it reduces overhead. Keep the codebase small and understandable.

## Main gameplay scene tree

Ministry (Node2D)
├── World
│   ├── TileMapLayer
│   ├── StaticProps
│   ├── Interactables
│   ├── NPCs
│   └── RoomTransitions
├── Player (CharacterBody2D)
├── GameSystems
│   ├── ObjectiveManager
│   ├── InventoryManager
│   ├── RegulationManager
│   └── QueueSystem
├── WorldUI
│   ├── InteractPrompt
│   └── FloatingNotifications
└── HUD (CanvasLayer)
    ├── ObjectiveTracker
    ├── InventoryPanel
    ├── CurrencyDisplay
    ├── ClosingTimer
    ├── DialogueBox
    └── PauseMenu

## Core systems and responsibilities

Player and interaction: Movement, nearby-object detection, prompts, and forwarding interactions. Must not contain quest or currency rules.

Objective manager: Tracks objective states, prerequisites, and progression; supplies the current objective to the HUD.

Inventory and currency: One source of truth for item quantities, stamps, forms, and brass tokens; supports add/remove/check/spend.

Regulation manager: Activates rules at predefined events. NPCs and machines ask it whether an action is currently permitted.

UI and dialogue: Displays objective changes, pickup notifications, fees, rejections, meetings, countdown, and ending. Does not decide permit validity.

Use autoloads only for truly global managers. Keep puzzle-specific and NPC-specific state on their own nodes. Use signals for UI updates and decoupled interactions.

# 8. Data-Driven Content

Store repeated content—item definitions, objective text, regulations, fees, and dialogue—in JSON or Godot Resources when this saves repetition. Each regulation should have a stable identifier, display name, activation trigger, and condition. Do not overengineer: small puzzle logic and the ending can remain simple scripts.

Example item fields: id, display_name, description, icon_path, stack_limit, tags. Example objective fields: id, description, prerequisites, completion_condition, next_objective_id.

# 9. Permit Quest Dependency Chain

Collect Form 27-B at the Department of Forms.

Acquire brass tokens and a queue ticket at Reception.

Obtain two required seals at the Stamp Office.

Power the pneumatic delivery system in the Steam Regulation Chamber.

Pass the Compliance Audit after a regulation changes.

Submit the final permit at the Registry.

Reveal: the target machine has been out of order since 1847; the permit was unnecessary.

# 10. Softlock Prevention

If the player spends all currency, provide a repeatable way to earn a small amount.

If a queue is missed, allow a new ticket.

If a regulation changes, communicate the new requirement and preserve access to necessary items.

If the closing timer expires, trigger an embarrassing penalty or overtime rather than making completion impossible.

If a critical item is lost or spent, provide a replacement or reset the relevant interaction.

The permit registry must validate all requirements before accepting the application.

Never trap the player permanently inside dialogue, meetings, doors, or minigames.

# 11. Visual and Audio Direction

## Blueprint visual specification

Background: dark navy or faded blueprint blue.

Walls/floors: thin cyan technical lines, grid patterns, labeled room boundaries.

Interactables: white/cyan outlines; brass/amber highlights on important objects.

UI: technical panels, calibration marks, numbered labels, mechanical readouts.

Characters: simplified silhouettes with distinctive hats, tools, or mechanical limbs.

Effects: steam puffs, gauge movement, stamp imprints, warning flashes.

Maintain strong text contrast. Confusing world signage must not make the objective tracker unreadable.

## Audio priorities

Mechanical ambience: gears, pneumatic tubes, steam, clanks.

Interface feedback: stamp impacts, rejection bells, ticket printing, notification chimes.

Comedy stingers: enormous fanfares for trivial accomplishments and dramatic sounds for mundane failures.

Use assets with compatible licenses and track credits. Do not spend hours composing an original soundtrack before core functionality is complete.

# 12. 48-Hour Milestone Schedule

| Time / phase | Work | Exit criterion |
| --- | --- | --- |
| 00–03h ¦ Foundation | Create Godot project and Git repo; player, floor, collision, camera, one test object, blueprint palette, basic UI, first test export. | Player moves and interacts with one object. |
| 03–08h ¦ Core loop | Objective manager, interaction interface, items/stamps, inventory/currency, form counter, stamp counter, permit registry, temporary ending. | Basic permit quest completes start to finish. |
| 08–14h ¦ Systems | Queue, closing timer, pressure puzzle, minigame, inspector, first regulation change. | Major interactions work and quest remains completable. |
| 14–21h ¦ Content | Connect six areas in one floor; NPCs, dialogue, signage, obstructions, meeting, 2–3 regulations. | Full level traversable; all objectives reachable. |
| 21–28h ¦ Presentation | Blueprint visuals, brass highlights, gauges, audio, cursed controls, strong dialogue. | Cohesive visual and comedic identity. |
| 28–35h ¦ Polish | Final reveal, credits, menu, restart, pause, timeout handling, UI feedback, dependency testing. | Complete game works without developer intervention. |
| 35–42h ¦ Stabilization | Full playthroughs, softlock testing, tuning, exported build verification. | Fresh player can reliably finish. |
| 42–48h ¦ Submission | Feature freeze, final build, clean launch test, screenshots/video, description, credits, backup, submit. | Submission delivered on time. |

## Scope gates

Review at hours 8, 14, 21, and 35. If late, cut optional mechanics rather than borrowing time from testing. Protect the last six hours from new features.

# 13. Antigravity Development Workflow

Define one task with exact files, APIs, acceptance criteria, and constraints.

Ask Antigravity to inspect the existing project before editing.

Generate one coherent feature at a time; do not request the whole game in one prompt.

Review diffs for API compatibility, signal names, node paths, and duplicated managers.

Run Godot parse/headless checks when available and launch the game to test real behavior.

Commit each working milestone; revert broken experiments instead of layering patches.

Do not accept claims of successful testing unless the tests were actually run.

## Reusable feature prompt

Implement the next feature in my Godot 4 GDScript game, Ministry of Mechanical Affairs.

Before editing:
- Inspect the existing project structure, relevant scripts, scene trees, and project input settings.
- Reuse existing systems instead of creating duplicate managers.
- Preserve existing working behavior.

Requirements:
- Implement only the requested feature and its necessary integration.
- Use typed GDScript where practical.
- Use signals for decoupled UI and gameplay updates.
- Avoid unnecessary dependencies, complex abstractions, and unrelated refactors.
- Handle invalid interactions and missing requirements gracefully.
- Do not silently change public methods, signal names, node paths, shared data formats, or input actions.

After editing:
1. List the files changed and explain why.
2. Describe any scene setup or editor actions still required.
3. Run an available Godot parse/headless check, or clearly state if this could not be run.
4. Identify edge cases and provide a short manual test checklist.
5. Do not claim that the feature works unless it has actually been tested.

Feature to implement: [DESCRIBE ONE FEATURE]

Acceptance criteria:
- [CRITERION 1]
- [CRITERION 2]
- [CRITERION 3]

## Non-negotiable rules

One source of truth: inventory lives in one inventory manager.

No untested bulk rewrites: test immediately after changes touching multiple systems.

Version control after every working milestone.

A successful parse is not proof that the quest is completable; verify manually.

# 14. Testing Checklist

## Core functionality

☐ Player movement and collision work.

☐ Nearby interaction prompts appear/disappear correctly.

☐ Quest objectives update in the HUD.

☐ Items can be collected and required stamps are recognized.

☐ Permit can be submitted when all conditions are met.

☐ Ending and restart work.

## Mechanics

☐ Queue can be joined, missed, and rejoined.

☐ Pressure puzzle has a valid solution and clear feedback.

☐ Regulation changes are communicated.

☐ Inspector checks the correct requirements.

☐ Currency cannot become unintentionally negative.

☐ Closing timer and timeout behavior work.

## Softlock prevention

☐ Critical items cannot be permanently lost.

☐ Required items can be recovered if lost/spent.

☐ Dialogue and meetings cannot permanently trap the player.

☐ Player can recover from a missed queue.

☐ Final permit remains obtainable after rule changes.

## Presentation and submission

☐ Controls are explained on the first screen.

☐ Objective text is readable against blueprint background.

☐ Important objects are identifiable.

☐ Audio and UI feedback work.

☐ Fresh launch reaches the main menu without errors.

☐ Exported build completes a full playthrough.

# 15. Fallback Scope

Tier 1 — Must ship: One compact level, movement, interaction, inventory, stamps, one puzzle, permit workflow, dialogue, final reveal, menu, restart, basic audio.

Tier 2 — If time permits: Queue, inspector, currency, escalating regulations, countdown, mechanical minigame, blueprint UI, excellent dialogue.

Tier 3 — Cut first: Multiple endings, elaborate physics, complex inventory shapes, extensive branching dialogue, extra floors, advanced control sabotage.

# 16. Submission Checklist

☐ Confirm the game starts from a clean launch.

☐ Verify the entire permit quest and final reveal in the exported build.

☐ Check keyboard controls and any required settings.

☐ Ensure the build does not depend on local absolute file paths.

☐ Include credits and license information for third-party assets.

☐ Capture requested screenshots or gameplay footage.

☐ Prepare a concise game description and controls.

☐ Keep a backup of the final build and source.

☐ Submit before the deadline; do not add features during the final six hours.

# 17. Immediate Next Steps

Create the Godot project and initialize Git.

Write GDD.md with premise, controls, core loop, six areas, and permit quest.

Write ARCHITECTURE.md with scene tree and public methods/signals of the core systems.

Build the movement-and-interaction prototype.

Complete the vertical slice: collect a form, obtain a stamp, submit permit, trigger ending.

Only then expand into queue, puzzle, inspector, and optional mechanics.

# Final Principle

Automate the coding, not the verification.

Antigravity can generate systems quickly, but the developer remains responsible for integration, playability, tone, and submission quality. A complete eight-minute game with a strong punchline beats an ambitious unfinished game.